## Instructions
SLOT ERP — Parallel-Run & Go-Live Tracker
Purpose: operationalize the go-live criteria from SLOT_PreLaunch_Checklist.md into something that gets
actually filled in week by week, rather than a static list nobody revisits.
How to use each tab:
• Go-Live Criteria — the five top-level gates. All five need to be "Done" before treating SLOT ERP as
the sole daily system of record with no fallback. Update Status and Date as each closes.
• Accountant Observations — the pre-launch checklist references "eight open observations" but only
names five specifically (control accounts, vendor/client data quality, exchange rates, missing
clients, AP name corrections). The other three are listed as blank rows — confirm the full list of
eight directly with the accountant rather than assuming these five are the whole set.
• Weekly Reconciliation — the core of the parallel run. One row per area per week. Type the SLOT ERP
figure and the Sage figure; Variance and % Variance calculate automatically. Row 5 (shaded) is a
worked EXAMPLE showing the expected format — delete or overwrite it, don't leave it mixed in with
real figures. Duplicate the 6-area block for each additional week (one month minimum = ~4 blocks).
• Rollback Plan — fill in and get both sides to sign before cutover, not after.
Color key: blue text = type your own value here. Black text = calculated automatically, do not overwrite.
Yellow shading = worked example — for format reference only.

## Go-Live Criteria
Go-Live Criteria
All five required — not most of these. Per SLOT_PreLaunch_Checklist.md.
# | Criterion | Status | Date Confirmed | Notes
1 | Section 1 fully checked — RLS confirmed enabled + FORCED on both company_data and app_users | Not Started
2 | All eight accountant observations confirmed closed (not "in progress") | Not Started
3 | One full parallel-run period completed — numbers reconciled or discrepancies explained | Not Started
4 | Accountant has signed off specifically on Section 4 (depreciation, FX reval, credit limits, Terminal Ops, control accounts, trial balance/aging) | Not Started
5 | Rollback plan agreed before cutover, not after | Not Started

## Accountant Observations
Accountant Observations
The checklist references eight; only five are named in the source docs. Confirm the rest with the accountant directly.
# | Observation | Status | Confirmed By | Date | Notes
1 | Control accounts reconcile correctly | Open
2 | Vendor / client data quality | Open
3 | Exchange rates | Open
4 | Missing clients | Open
5 | AP name corrections | Open
6 | (unconfirmed — ask accountant for #6) | Open
7 | (unconfirmed — ask accountant for #7) | Open
8 | (unconfirmed — ask accountant for #8) | Open

## Weekly Reconciliation
Weekly Reconciliation
One row per priority area per week. Reconcile weekly, not just at period end — catching a discrepancy after 3 days is cheap; after 30 is not.
Week # | Week Starting | Priority Area | SLOT ERP Figure (₦) | Sage Figure (₦) | Variance (₦) | % Variance | Explained? | Explanation / Notes | Reconciled By | Date Signed
1 | EXAMPLE | Depreciation postings (sample of fixed assets) | 1250000 | 1250000 | 0 | 0% | Y
1 | EXAMPLE | FX revaluation (unrealized G/L, 2-3 FC balances) | 84500 | 82000 | 2500 | 3.049% | N | Timing difference on FX rate applied — confirm with accountant
1 | EXAMPLE | Credit limit overrides (activity log attribution) | 0 | 0 | 0 | - | Y
1 | EXAMPLE | Terminal Ops (standalone P&L/BS, one full BoL lifecycle) | 3400000 | 3400000 | 0 | 0% | Y
1 | EXAMPLE | Control accounts (2001-2005, 6002, 7001) | 42500000 | 42500000 | 0 | 0% | Y
1 | EXAMPLE | Trial balance + AR/AP aging | 127750000 | 127750000 | 0 | 0% | Y
2 |  | Depreciation postings (sample of fixed assets)
2 |  | FX revaluation (unrealized G/L, 2-3 FC balances)
2 |  | Credit limit overrides (activity log attribution)
2 |  | Terminal Ops (standalone P&L/BS, one full BoL lifecycle)
2 |  | Control accounts (2001-2005, 6002, 7001)
2 |  | Trial balance + AR/AP aging
3 |  | Depreciation postings (sample of fixed assets)
3 |  | FX revaluation (unrealized G/L, 2-3 FC balances)
3 |  | Credit limit overrides (activity log attribution)
3 |  | Terminal Ops (standalone P&L/BS, one full BoL lifecycle)
3 |  | Control accounts (2001-2005, 6002, 7001)
3 |  | Trial balance + AR/AP aging
4 |  | Depreciation postings (sample of fixed assets)
4 |  | FX revaluation (unrealized G/L, 2-3 FC balances)
4 |  | Credit limit overrides (activity log attribution)
4 |  | Terminal Ops (standalone P&L/BS, one full BoL lifecycle)
4 |  | Control accounts (2001-2005, 6002, 7001)
4 |  | Trial balance + AR/AP aging

## Rollback Plan
Rollback Plan
Agree this BEFORE cutover, not after.
Current system (Sage) stays available until
Who can trigger a rollback (name / role)
Condition that triggers rollback | e.g. trial balance doesn't tie out within [X] for two consecutive weeks
Agreed by — SLOT Engineering (name, title)
Agreed by — Mollernik Global Services (name, title)
Date agreed